## Summary
HighFly Flutter Application - Work Summary
Phase | Start Date | End Date | Duration (Days) | Hours
Phase 1: Project Initialization & Foundation | 2025-10-07 | 2025-10-08 | 2 | 6
Phase 2: Core Booking System Development | 2025-10-09 | 2025-10-10 | 2 | 45
Phase 3: API Integration & Booking Enhancements | 2025-10-15 | 2025-10-27 | 13 | 44
Phase 4: Feature Expansion & UI Improvements | 2025-11-05 | 2025-11-25 | 21 | 78
Phase 5: Web Platform Support & Major Enhancements | 2025-12-12 | 2025-12-26 | 15 | 92
Phase 6: Code Quality & Bug Fixes | 2025-12-31 | 2026-01-07 | 8 | 56
TOTAL | 2025-10-07 | 2026-01-07 | 61 | 321
Notes:
1. All time estimates are based on manual development by a mid-level developer
2. Hours shown are direct development hours only
3. Additional overhead (testing, debugging, meetings) estimated at ~38% of direct hours

## Work Summary
Phase | Task | Start Date | End Date | Hours
Phase 1: Project Initialization & Foundation | Project Setup & Initial Configuration | 2025-10-07 | 2025-10-08 | 4
| Initial Commit & Repository Setup |  |  | 2
Phase 1: Project Initialization & Foundation - TOTAL |  | 2025-10-07 | 2025-10-08 | 6
Phase 2: Core Booking System Development | Booking Process Implementation | 2025-10-09 | 2025-10-10 | 8
| Comprehensive 5-Step Booking Flow |  |  | 16
| Hold Details Step Integration |  |  | 4
| Profile Module Implementation |  |  | 6
| UI/UX Theming & Styling |  |  | 4
| Booking Flow UI Updates |  |  | 4
| Bug Fixes & Code Cleanup |  |  | 3
Phase 2: Core Booking System Development - TOTAL |  | 2025-10-09 | 2025-10-10 | 45
Phase 3: API Integration & Booking Enhancements | Product List API Implementation | 2025-10-15 | 2025-10-27 | 8
| Available Plots API Implementation |  |  | 8
| Comprehensive Booking System Enhancement |  |  | 12
| Enhanced Visit Management System |  |  | 10
| UI/UX Improvements for Booking System |  |  | 6
Phase 3: API Integration & Booking Enhancements - TOTAL |  | 2025-10-15 | 2025-10-27 | 44
Phase 4: Feature Expansion & UI Improvements | UI Updates & Feature Enhancements | 2025-11-05 | 2025-11-25 | 10
| Bookings and Holds Management Features |  |  | 16
| Logout Confirmation Dialog |  |  | 2
| Form 16 PDF Upload & Location Icon Updates |  |  | 4
| OTP Verification Flow Implementation |  |  | 10
| Hold-to-Booking Conversion Feature |  |  | 8
| Tenant API Keys Implementation |  |  | 6
| Plot Model Enhancement |  |  | 4
| Organization Feature Implementation |  |  | 10
| UI and Authentication/Booking Flow Improvements |  |  | 8
Phase 4: Feature Expansion & UI Improvements - TOTAL |  | 2025-11-05 | 2025-11-25 | 78
Phase 5: Web Platform Support & Major Enhancements | Hold Edit Functionality | 2025-12-12 | 2025-12-26 | 10
| Error Handling Improvements |  |  | 6
| CORS Web Fix Implementation |  |  | 4
| Web Platform Support - Initial Implementation |  |  | 12
| UI Responsiveness Improvements |  |  | 16
| Major UI/UX Improvements |  |  | 24
| Web Platform Support Enhancements |  |  | 8
| Project Screens Implementation |  |  | 12
Phase 5: Web Platform Support & Major Enhancements - TOTAL |  | 2025-12-12 | 2025-12-26 | 92
Phase 6: Code Quality & Bug Fixes | Deprecated Code Resolution | 2025-12-31 | 2026-01-07 | 6
| Code Cleanup & Warning Removal |  |  | 16
| QA Feedback Implementation |  |  | 8
| Web App Bug Fixes |  |  | 10
| Base URL Configuration Updates |  |  | 2
| URL Configuration Updates |  |  | 2
| Notification System Implementation |  |  | 12
Phase 6: Code Quality & Bug Fixes - TOTAL |  | 2025-12-31 | 2026-01-07 | 56
GRAND TOTAL |  | 2025-10-07 | 2026-01-07 | 321